## Slide 1
EDUTRACK
Implementation Plan
Java 21 · Spring Boot 3.3 · MySQL 8.4 · React 18 + TypeScript
PostgreSQL → MySQL translation · milestones M0–M7 · 18 weeks
Build specification — companion to the Product Blueprint v1.2

## Slide 2
Two documents, two authorities
Where they disagree, each wins in its own domain — and nothing is silent
THE BLUEPRINT
The product specification
What the system does. Every screen, every field, every rule.
Wins on BEHAVIOUR.
THIS PLAN
The build specification
What stack, what order, what has to be decided first.
Wins on IMPLEMENTATION.
WHY THIS MATTERS HERE
The blueprint recommends NestJS + PostgreSQL. We are building on Java + MySQL.
That means its DDL, its BullMQ / Socket.IO / SheetJS choices and its shared-Zod-schema guidance do not apply as written. Every substitution is listed explicitly — none are left for a developer to discover mid-sprint.
Implementation Plan
1

## Slide 3
Three things are the architectural spine
Everything else hangs off them, and each is expensive to retrofit
01
The append-only history model
ticket_history, ticket_effort_logs and ticket_stage_transitions are insert-only, hash-chained, enforced at four independent layers — service, DB grants, DB triggers, and absent HTTP routes.
Built late, every write path already written has to be re-audited.
02
The Workflow Ribbon
Eight configurable stages, cycle_no and iteration_no as two orthogonal counters, per-stage-per-resource effort attribution, and the active-vs-idle split that makes it more than decoration.
The product differentiator, and the hardest UI in the system.
03
The row-scope guard
Every ticket query rewritten server-side with a mandatory scope predicate. Developer sees assigned_to = me; PM sees their projects; out-of-scope IDs return 404, not 403.
One leak here and the system fails its first audit.
Implementation Plan
2

## Slide 4
The stack
Layer | Choice | Note
Language · Framework | Java 21 LTS · Spring Boot 3.3+ | Virtual threads for the IMAP poller and mail workers
Persistence | Spring Data JPA + Hibernate 6 · Flyway | JdbcTemplate for reporting queries; migrations hand-written SQL
Database | MySQL 8.4 · InnoDB · utf8mb4 | All timestamps DATETIME(6) in UTC
Cache · Scheduler | Redis 7 · @Scheduled + ShedLock | Token registry, rate limits; ShedLock stops double-firing
Async · Realtime | Transactional outbox · Spring WebSocket + STOMP | Redis relay for multi-instance fan-out
Storage · Excel · Mail | MinIO/S3 · Apache POI · Spring Mail + Thymeleaf | POI streaming, not the DOM reader
Security | Argon2id · Nimbus JOSE JWT | 64 MB memory, 3 iterations
Frontend | React 18 + TS + Vite · Tailwind + shadcn/ui | TanStack Query · Zustand · RHF + Zod · Recharts
Contract | springdoc-openapi → generated TS client | CI fails if the committed client is stale
Testing | JUnit 5 · Testcontainers · MockMvc · ArchUnit | ArchUnit enforces the scope-guard rule structurally
Implementation Plan
3

## Slide 5
Five Node choices with no Java equivalent
Each substitution preserves the behaviour the blueprint specifies
Blueprint says | We use | Why, and what changes
BullMQ | Transactional outbox + @Scheduled + ShedLock | email_log already IS an outbox — status, retry_count, provider ID. Claim rows with SELECT … FOR UPDATE SKIP LOCKED. Enqueue becomes atomic with the business transaction, which BullMQ could not have guaranteed.
Socket.IO | Spring WebSocket + STOMP, Redis relay | Rooms map to destinations. Subscriptions authorised in a ChannelInterceptor using the same scope rules as REST — a Developer cannot subscribe to a ticket they could not GET.
SheetJS | Apache POI — SXSSF write, SAX read | The streaming reader is required, not optional: POI's DOM reader loads a 5,000-row workbook fully into memory per concurrent import.
Prisma / TypeORM | Spring Data JPA + Flyway | Migrations are hand-written SQL, which we want anyway — the immutability triggers are not expressible through a migration generator.
Shared Zod schemas | OpenAPI → orval codegen | The one genuine loss. Bean Validation on the Java DTOs is the single source of truth; springdoc emits it; codegen produces Zod. CI fails on a stale client, so drift is caught at merge.
Implementation Plan
4

## Slide 6
PostgreSQL → MySQL · type and construct mapping
Eight constructs do not exist in MySQL 8 — this mapping is normative for every migration
Blueprint (PostgreSQL) | MySQL 8 equivalent | Note
BIGSERIAL PRIMARY KEY | BIGINT AUTO_INCREMENT PRIMARY KEY | 
TIMESTAMPTZ | DATETIME(6), stored UTC | TIMESTAMP has a 2038 limit and silent session-timezone conversion
VARCHAR(20)[] · BIGINT[] | JSON | Validated in the service layer; queried with JSON_CONTAINS
Partial index WHERE … | Stored generated column + plain index | pcd_open, current_ticket_id
UPDATE … RETURNING | LAST_INSERT_ID(expr) idiom | Atomic, connection-local, no explicit row lock needed
RAISE EXCEPTION in a function | SIGNAL SQLSTATE '45000' per trigger | MySQL needs TWO triggers where Postgres allowed one
CHAR(64) hashes | CHAR(64) COLLATE ascii_bin | Exact comparison, no utf8mb4 overhead
Boolean · NUMERIC(p,s) | TINYINT(1) · DECIMAL(p,s) | 
Ticket ID generation: UPDATE projects SET ticket_seq = LAST_INSERT_ID(ticket_seq + 1) WHERE id = ?; then SELECT LAST_INSERT_ID();
COUNT(*) must never be used — it breaks silently, and only under concurrency.
Implementation Plan
5

## Slide 7
Four defects found in the blueprint itself
These are in the source document, not artefacts of the MySQL move
The effort roll-up double-counts after a reopen
→ Add AND e.cycle_no = t.cycle_no to the join.
§4A.5's LEFT JOIN matches effort logs on (ticket_id, stage_code, iteration_no) but omits cycle_no. A ticket that re-enters the same stage at the same iteration in cycle 2 absorbs cycle 1's hours.
The same query will not run on MySQL at all
→ Rewrite with every non-aggregated column in GROUP BY — do not disable the mode, it catches real bugs.
It selects five non-aggregated columns while grouping by three. PostgreSQL permits it via functional dependency; MySQL's ONLY_FULL_GROUP_BY rejects it.
ticket_stage_transitions is under-protected
→ A BEFORE UPDATE trigger permitting only the seal, using NULL-safe <=> comparison.
§4A.5 creates only a BEFORE DELETE trigger and mentions an unspecified CHECK for exited_at — leaving every other column freely updatable by a stray query or ORM dirty-check.
The hash chain forks under concurrency
→ Chain per-ticket, behind SELECT … FOR UPDATE on the ticket row.
§4.2 specifies prev_hash/row_hash and nightly verification but never says how two concurrent appends stay linear. They don't — both read the same latest row, and the verifier reports our own bug as tampering.
Implementation Plan
6

## Slide 8
Immutability in MySQL
Triggers, their three limits, and what closes each
CREATE TRIGGER trg_hist_no_update BEFORE UPDATE ON ticket_history
FOR EACH ROW
BEGIN
SIGNAL SQLSTATE '45000'
SET MESSAGE_TEXT = 'Immutable table: ticket_history
rows cannot be updated';
END
-- and a second, identical trigger for BEFORE DELETE
-- MySQL cannot express BEFORE UPDATE OR DELETE
Triggers do not fire on TRUNCATE
The app DB user is granted no DROP privilege, which TRUNCATE requires
Triggers do not survive DROP TABLE
No DDL privileges for the app user; Flyway runs as a separate migration user
A privileged user can drop the triggers
The hash chain is the backstop — tampering that bypasses triggers still breaks the chain
THE ONE PERMITTED MUTATION
Sealing a stage transition: exited_at goes NULL → timestamp, and duration_mins is computed at the same moment.
The trigger permits it only when the row is still open AND only those columns changed — compared with <=>, because plain = returns NULL for two NULLs and silently passes the check.
Implementation Plan
7

## Slide 9
Every deviation from the blueprint, in one place
Nothing is silent
# | Blueprint | What we do instead | Why
D-1 | NestJS / Node backend | Spring Boot / Java | Directed by the team
D-2 | PostgreSQL 16 | MySQL 8.4 | Directed by the team
D-3 | BullMQ, Socket.IO, SheetJS, Prisma | Outbox, STOMP, POI, JPA+Flyway | No Java equivalents
D-4 | Shared Zod schemas | OpenAPI + generated client, CI check | Cannot share validation across languages
D-5 | DELETE trigger + unspecified rule | Explicit BEFORE UPDATE seal-only trigger | Every other column was left updatable
D-6 | Hash chain, concurrency unspecified | Per-ticket chain with row lock | Concurrent appends fork the chain
D-7 | Roll-up query as written | Rewritten + cycle_no added to join | Original double-counts after a reopen
D-8 | Ticket ID year behaviour unstated | No reset at rollover; code immutable | Resetting creates a midnight collision window
D-9 | Phases 0–6 by calendar | Milestones M0–M7 by dependency | Each milestone independently demoable
Implementation Plan
8

## Slide 10
Four decisions must be locked before M2
Blueprint §16 lists 13 governance questions — nine can wait, these four change the schema
# | Question | Proposed default | What it touches
G-1 | Is effort mandatory at handoff — blocking or warn-only? | Blocking, per-project flag defaulting on | Handoff DTO, S-29, skip report
G-2 | Does a rework loop reset the Planned Close Date? | No — the original date stands | SLA scanner, breach reporting
G-3 | Can a Developer close, or only mark Resolved? | Resolved only | workflow_transitions seed, S-23
G-4 | Does an auto-escalated level revert after closure? | No — original_level preserved, both reported | Already in schema; needs the report
OPEN QUESTION THE BLUEPRINT DOES NOT ANSWER
Is there an existing employee directory or SSO — Azure AD, Google Workspace — that the Resource Master should sync from, or is EduTrack the system of record for users?
If a directory exists, users needs an external ID from M1, not after M3.
Implementation Plan
9

## Slide 11
Milestones — sequenced by dependency, not calendar
Each ends in something demoable, with explicit exit criteria
 | Milestone | Scope | Exit criterion
M0 | Foundation | Monorepo, Docker Compose, the complete schema in one pass, triggers, seeds, design tokens, CI | docker compose up gives a migrated, seeded DB
M1 | Auth + scope guard | Argon2id login, JWT + refresh rotation with family revocation, the three guards, permission matrix | All six roles land correctly; Developer gets 404
M2 | Immutability core | Insert-only services, canonical JSON, per-ticket hash chain, nightly verifier, negative tests | Verifier passes; no fork under concurrent load
M3 | Masters | 13 master screens, client master, the import wizard built once and registered twice, working calendar | Admin can stand up a tenant without touching the DB
M4 | Tickets + ribbon | Ticket CRUD, cycles, reopen, comments, attachments, transition service, ribbon, Journey grid | Walkthrough A reconciles to 38.0 h, 3 iterations
M5 | Engines | SLA + stage-SLA scanners on the working calendar, escalation, mail engine, notification centre | Scanner escalates, mails, turns the banner red live
M6 | Dashboard + reports | Pre-aggregated summary tables, 20 widgets with drill-down, 18 reports with export | First paint under 1.5 s at 50,000 tickets
M7 | Chat + hardening | STOMP chat, Ask Status, then CSP, scanning, load test, penetration test, UAT | Security review passes; UAT signed off
Implementation Plan
10

## Slide 12
Testing strategy
Weighted toward the three risks the blueprint identifies as most expensive
Layer | Tooling | What it must cover
Unit | JUnit 5 + AssertJ | SLA maths on the working calendar, effort roll-ups, iteration/cycle counters, hash canonicalisation
Integration | Testcontainers | Every migration against real MySQL; triggers proven by negative tests; reopen and handoff transactions
Permission matrix | Parameterised MockMvc | Every role × every route. A new route without a matrix entry fails the build
Architecture | ArchUnit | No controller reaches a repository directly; no update/delete method exists on append-only services
Concurrency | Custom harness | Parallel ticket creation (no duplicate codes); parallel appends (no chain fork); parallel handoffs
Contract | springdoc + codegen diff | CI fails if the committed TypeScript client is stale against the spec
End-to-end | Playwright | Walkthroughs A, B and C from blueprint §14, against a seeded database
Performance | k6 | Dashboard and ticket-list p95 on a 50,000-ticket dataset
Implementation Plan
11

## Slide 13
Risks carried, and four specific to this stack
Stack-specific risk | Mitigation
MySQL trigger protection bypassed by a privileged user | The hash chain is the backstop; nightly verification; the app user holds no DDL privilege
Generated-column indexes underperform Postgres partial indexes as data grows | Benchmark the SLA scan at M5 against 500,000 rows; partition tickets by year if needed
OpenAPI client drift between Java and TypeScript | CI staleness check fails the build; Bean Validation is the single source of truth
Outbox worker falls behind under mail burst | SELECT … FOR UPDATE SKIP LOCKED allows horizontal worker scaling; email_log depth is a Prometheus alert
PLUS THE BLUEPRINT'S OWN REGISTER, UNCHANGED
History integrity challenged in a dispute · notification fatigue · dashboard slowdown · under-logged effort · role-scope leakage · ribbon unreadable at 8 stages · teams gaming the stage clock · missed alerts · client import corruption · malicious uploads · internal notes leaking to a client.
Implementation Plan
12

## Slide 14
What happens next
IMMEDIATE NEXT STEP · M0
Repo scaffold, Docker Compose, the complete Flyway migration set translated per §3, seed data, and the design tokens — a running, migrated stack to inspect before any feature work begins.
BLOCKING ON NOTHING
The four governance decisions are needed before M2, not before M0.
The SSO / directory question is needed before M1.
PLAN.md · TEAM-PLAN.md · GETTING-STARTED.md · docs/streams/STREAM-A…D.md