## Slide 1
EDUTRACK
Team Structure, Work Division
& Git Workflow
Four developers · four vertical streams · 18 weeks
Java 21 · Spring Boot · MySQL 8.4 · React 18
Companion to PLAN.md and the Product Blueprint v1.2

## Slide 2
The problem this plan solves
Four developers on one codebase produce three predictable failures
01
The blocking chain
PLAN.md sequences M0 → M1 → M2 → M3/M4 by dependency. Read literally, three developers sit idle for six weeks waiting on the schema and the security spine.
→ Sprint 0 + three decouplers
02
Merge collisions
A conventional Spring layout puts every controller in one folder. Four developers then edit the same four directories every single day.
→ Feature packaging + ownership map
03
Contract drift
Four people building against an API that does not exist yet will each assume a different shape for it, and discover the mismatch in week eight.
→ OpenAPI spec as a Sprint 0 deliverable
EduTrack — Team Plan
2

## Slide 3
The four streams
Vertical ownership — each developer owns their slice from database to screen
 | Stream | Owns | Milestones
A | Platform & Security | Schema, migrations, auth, the scope guard, immutability core, CI/CD, then dashboard & reports | M0 · M1 · M2 · M6
B | Masters & Clients | All 13 master screens, client master, Excel import, working calendar, workflow template designer | M3 → joins C
C | Tickets & Ribbon | Ticket CRUD, detail page, cycles/reopen, comments, attachments, the Workflow Ribbon, Journey grid | M4
D | Engines & Realtime | SLA & escalation scanners, mail engine, notification centre, WebSocket infrastructure, chat | M5 · M7
Why vertical, not 2 backend + 2 frontend: a horizontal split makes every feature need two people to coordinate before it can ship — and idles the frontend developer whenever the backend one is behind.
EduTrack — Team Plan
3

## Slide 4
Who should take which stream
The assignment matters more than the plan — two of these four are load-bearing
A · Platform & Security
Your strongest backend and infrastructure person.
Everything else depends on their first six weeks, and the scope guard is the highest-risk component in the system. They are also the natural schema arbiter.
C · Tickets & Ribbon
Your strongest all-rounder.
The largest slice — roughly 40% of the product surface and the hardest UI in it. Stream B joins them from week 10.
B · Masters & Clients
Fastest at CRUD and forms.
Broad but shallow: many screens, few hard problems. The Excel import wizard is the one genuinely tricky piece.
D · Engines & Realtime
Comfortable with async and scheduling.
The most independent — workers, queues and sockets touch little of the request path. Least damaged by a slightly later start.
EduTrack — Team Plan
4

## Slide 5
Sprint 0 · weeks 1–2 — nobody waits
Each stream has two weeks of work that depends on nothing anyone else is writing
 | Sprint 0 deliverable | Depends on
A | Maven multi-module skeleton · docker-compose (MySQL, Redis, MinIO, Mailpit) · the complete Flyway baseline schema — all ~28 tables, triggers, indexes · CI pipeline · DB users and grants | Nothing
B | All seed data — 6 roles + permission matrix, 11 task types, 4 priorities, statuses, 3 workflow templates · JPA entities and repositories · the ticket fixture corpus | A's schema, day 3
C | React scaffold · design tokens from blueprint §12.1 · the shared component library — button, table, chip, modal, slide-over, toast, skeleton · Storybook · app shell | Nothing
D | The OpenAPI contract for every endpoint in blueprint §13 · codegen pipeline · MSW mock server with realistic fixtures · the CI staleness check | Nothing
Why one person writes the schema: 28 interlocking tables authored by four people produce four naming conventions, four opinions on nullability, and a conflict on every migration file.
EduTrack — Team Plan
5

## Slide 6
Three decouplers keep the streams independent
Without these, the dependency chain serialises the team — one person works, three wait
Mock server
OWNED BY D · SPRINT 0
Every frontend feature is developed against MSW handlers generated from the OpenAPI spec.
Stream C builds the entire ticket detail page — ribbon, tabs, journey grid — before a single ticket endpoint exists.
dev-noauth profile
OWNED BY A · DAY 10
A Spring profile injecting a configurable fake principal: role, project list, reportee list.
B, C and D develop against realistic scope behaviour four weeks before the real guard lands. Rejected outside local; disabled in CI.
Seed fixtures
OWNED BY B · SPRINT 0
200 tickets across 3 projects — varied stages, iterations, cycles and breach states.
D tests the SLA scanner and C tests the ribbon before either feature exists. Build once, use everywhere.
EduTrack — Team Plan
6

## Slide 7
Phase timeline · 18 weeks
Consistent with the blueprint's own five-month estimate
Wk | A — Platform | B — Masters | C — Tickets | D — Engines
1–2 | M0 scaffold, schema, CI | Seed data, entities, fixtures | Design system, Storybook | OpenAPI contract, mocks
3–5 | M1 auth, JWT, rotation | S-07–S-12 core masters | S-19 create, S-17 list | Outbox, scheduler, STOMP
6–7 | M1 scope guard + matrix | S-32–S-34 clients + import | S-20 detail, S-21 quick update | M5 SLA + stage-SLA scanners
8–9 | M2 immutability, hash chain | S-13/S-30 workflow designer | M4 cycles, comments, attachments | M5 escalation, mail engine
10–11 | M6 aggregation + dashboard | joins C — ribbon UI | M4 handoff, Journey grid | M5 notifications, S-26
12–14 | M6 widgets, drill-down | M6 reports + exports | M4 S-22/23/24/29/31 | M7 chat, Ask Status
15–16 | Performance, S-16 audit | S-28 Resource 360 | E2E walkthroughs A/B/C | M7 finish, live ribbon
17–18 | Security review, go-live | UAT fixes | UAT fixes | UAT fixes
The one hard dependency: A's scope guard lands week 7. Until then B, C and D must NOT write their own filtering as a workaround — that becomes a permanent security hole.
EduTrack — Team Plan
7

## Slide 8
Code ownership map
Feature packaging, not layer packaging — so a stream's work lives where nobody else touches
backend/
common/ → A shared DTOs, hashing, OpenAPI
domain/db/migration/ → A Flyway — schema arbiter
api/security/ → A filter chain, scope resolver
api/feature/auth|dashboard|reports/ → A
api/feature/masters|clients|imports/ → B
api/feature/workflow/ → B (C consumes, B owns)
api/feature/tickets/ → C CRUD, cycles, comments
api/feature/transitions/ → C handoff, ribbon, journey
api/feature/notifications|chat/ → D
api/realtime/ → D STOMP, interceptor, topics
worker/ → D (A owns hash verifier)
frontend/src/
components/ui/ → C additive changes only
components/ribbon/ → C
styles/tokens.css → C frozen after Sprint 0
api/generated/ → nobody — generated, never edited
features/auth|dashboard|reports/ → A
features/masters|clients/ → B
features/tickets/ → C
features/chat|notifications/ → D
The default Spring layout puts every controller in one folder.
Four developers then edit that folder daily — which is exactly how a team of four ends up moving like a team of one.
THE RULE
Work only in your stream's paths.
Touching another stream's directory needs that owner's sign-off — say so, rather than editing it quietly.
This map becomes CODEOWNERS.
EduTrack — Team Plan
8

## Slide 9
Conflict hotspots — and the rule for each
Seven files will otherwise conflict on most merges
File | Why it conflicts | The rule
Flyway migrations | Sequential V14__ numbering collides whenever two developers add a migration the same day | Timestamp versioning: V20260812_1430__desc.sql · never edit an applied file
Generated API client | A large generated tree that conflicts constantly and is meaningless to merge by hand | On any conflict take neither side — regenerate. .gitattributes merge=ours
Seed data | One shared seed file guarantees four-way conflicts | One seed file per stream, loaded by a manifest A owns
Security config | Every stream wants to register its own routes and permissions | A owns the filter chain; streams contribute per-feature @Configuration
Design tokens | A stream adding its own colour drifts the palette across four features | Frozen after Sprint 0 — request a token from C, never add one
pom.xml / package.json | Two developers adding different JSON libraries in the same week | Announce dependency changes before committing; regenerate lockfiles
Shared components | C owns components/ui but all four consume it | Additive only. Storybook is the contract — not in Storybook, not shared
EduTrack — Team Plan
9

## Slide 10
Git branch model
Developers push to branches · Claude merges · then it reaches main
main protected · release-only · tagged
Claude promotes — nobody pushes
└── develop protected · integration
Claude merges — nobody pushes
├── feat/platform/jwt-refresh-rotation
├── feat/masters/client-excel-import
├── feat/tickets/ribbon-handoff-dialog
└── feat/engines/sla-scanner
WHY TWO PROTECTED BRANCHES
develop is where four streams actually integrate, and where conflicts surface.
main only ever receives a develop that is already proven green.
Merging four streams straight into main means resolving every conflict against your release branch.
NAMING · <type>/<stream>/<slug>
type feat · fix · chore · refactor · docs
stream platform · masters · tickets · engines
slug kebab-case, describes the change
CONVENTIONAL COMMITS
feat(tickets): add handoff dialog with effort confirmation
fix(engines): honour working calendar in stage-SLA check
EduTrack — Team Plan
10

## Slide 11
Rules for developers
Seven rules that make the integration job tractable
Branch from develop, never from main.
Rebase on develop daily — a branch unrebased for a week is a conflict waiting to become someone else's problem.
Small pull requests — target under 400 changed lines. A 3,000-line PR cannot be meaningfully reviewed.
No merge commits inside a branch — rebase, so conflicts are resolved once rather than replayed.
Push at least once a day, even work in progress. Unpushed work is invisible work.
CI must be green before requesting integration. Claude does not merge a red branch.
Never commit .env, credentials, application-local.yml, target/, node_modules/, .DS_Store.
BRANCH PROTECTION · main and develop
Direct pushes blocked · 1 approval required · status checks must pass · linear history · no force push · no deletion
EduTrack — Team Plan
11

## Slide 12
The integration procedure
What Claude runs — written down so it is repeatable, not ad hoc
PER BRANCH · DAILY
git fetch --all --prune
git checkout develop && git pull
git checkout feat/tickets/ribbon-handoff
git rebase develop # conflicts resolved here
mvn -q verify
npm --prefix frontend run build && npm test
git checkout develop
git merge --no-ff feat/tickets/ribbon-handoff
git push origin develop
--no-ff is deliberate: it keeps each feature visible as a unit, which matters when a milestone has to be bisected or reverted.
PRE-MERGE CHECKLIST
CI green on the branch
No edits to another stream's paths without sign-off
No changes to already-applied migrations
Append-only tables still have no update or delete path
New endpoints in the OpenAPI spec; client regenerated
Tests exist; new routes have permission-matrix entries
No secrets, no PII in logs, no stray debug output
On genuinely ambiguous conflicts — two streams changing the same business rule in different directions — the branch is handed back with the question, not guessed at.
EduTrack — Team Plan
12

## Slide 13
Cadence and promotion to main
When | What happens | Who
Continuously | Developers push to their feature branches | Developers
Daily · end of day | Claude integrates all ready branches into develop | Claude
Daily · next morning | Anything unmergeable is reported back with the specific conflict | Claude
Weekly / milestone end | Claude promotes develop → main and tags the release | Claude
PROMOTION
git checkout develop && git pull
mvn -q verify && npm --prefix frontend run build
# smoke test against a fresh docker compose stack
git checkout main && git merge --no-ff develop
git tag -a v0.3.0 -m "M3 — master data module"
git push origin main --tags
main should always be deployable.
If it isn't, the promotion gate failed — and that is the thing to fix.
EduTrack — Team Plan
13

## Slide 14
Repository bootstrap checklist
The project is not yet a git repository, and gh is not installed on this machine
1
git init, with develop as the working branch
2
.gitignore — Java, Node, IDE, OS, secrets
3
.gitattributes — generated client merge=ours, eol=lf
4
Move blueprint, PLAN.md, TEAM-PLAN.md into docs/
5
CODEOWNERS from the ownership map
6
CONTRIBUTING.md — the rules, condensed to one page
7
Pull request template
8
Initial commit on main; branch develop; push both
9
Create the remote, apply branch protection, add the team
10
.github/workflows/ci.yml — build, test, staleness check
Steps 1–8 can be done locally today. Step 9 needs the remote decided and either gh installed or the web UI. Step 10 lands with Stream A's Sprint 0 work.
EduTrack — Team Plan
14

## Slide 15
Definition of done
A branch is ready for integration when all ten hold
Feature works against the real backend, not only against mocks
Unit tests for business logic; integration tests for any new endpoint
New routes have permission-matrix entries for all six roles
Migrations use timestamp versioning; no applied file was edited
OpenAPI spec updated; client regenerated
Storybook entry for any new shared component
No new lint or compiler warnings
Screens match the design tokens; keyboard navigable; ARIA labels present
Rebased on current develop, CI green
Touches only the stream's owned paths, or has the other owner's sign-off
Developers never merge their own branch. Push it, say it is ready, and it enters the integration queue.
EduTrack — Team Plan
15

## Slide 16
What to do right now
1
Assign the four streams
Stream A must be your strongest backend person — they gate the other three for six weeks.
2
Answer the directory question
Does an employee directory or SSO already exist? If yes, users needs an external ID now, not after M3.
3
Bootstrap the repository
git init, .gitignore, docs/, CODEOWNERS, CONTRIBUTING.md, initial commit, branch develop. ~10 minutes.
4
Create the remote and add the team
Branch protection on both main and develop. Needs gh installed or the web UI.
5
Kickoff — 90 minutes, whole team
Walk blueprint §4A and §4 together. Four people need one shared mental model.
6
Everyone runs their stream skill
Sprint 0 begins. C and D start day 1; B starts day 3.
docs/TEAM-PLAN.md · docs/GETTING-STARTED.md · docs/streams/STREAM-A…D.md