## Slide 1
EDUTRACK
Ownership &
Dependency Map
Who does what · what blocks what · what runs at the same time
4 developers · 17 cross-stream dependencies · 18 weeks
docs/DEPENDENCIES.md

## Slide 2
Four vertical streams, one owner each
Each owns their slice from database to screen — not a backend/frontend split
A
Platform & Security
Shivendra
A-001 … A-075
Schema · migrations · auth · scope guard · immutability core · CI · dashboard · reports
B
Masters & Clients
Ayush
B-001 … B-063
Master screens · client master · Excel import · working calendar · workflow designer
C
Tickets & Ribbon
Divyansh
C-001 … C-064
Ticket CRUD · cycles · comments · attachments · the Workflow Ribbon · Journey grid
D
Engines & Realtime
Debashis
D-001 … D-059
OpenAPI contract · SLA scanners · mail engine · notifications · WebSocket · chat
Only 17 dependencies cross a stream boundary. Everything else is internal to one developer — which is the entire point of splitting the work this way.
Ownership & Dependencies
1

## Slide 3
Four dates decide whether this works
Everything else can slip a few days. These cannot — they are what makes four people work in parallel
Due | Task | What it is | Owner | If it is late
Day 5 | D-004 | MSW mock server | Debashis | Divyansh's entire frontend stalls
Day 10 | A-012 | dev-noauth profile | Shivendra | All three others stop
Day 10 | B-007 | Ticket fixture corpus | Ayush | No data to test ribbon or SLA against
Week 3 | B-024 | Working-hours service | Ayush | Debashis cannot start the SLA engine at all
WHY THESE FOUR AND NOT OTHERS
Each one unblocks somebody else rather than advancing its own stream. They are the decouplers — mocks let the frontend run ahead of the API, dev-noauth lets three people work before the security spine lands, and fixtures let two people test against data that does not exist yet.
Ownership & Dependencies
2

## Slide 4
The 17 cross-stream dependencies · 1 of 2
Every edge where one developer waits on another
# | Blocker | What it is | Who waits on it | Needed
1 | A-002 | docker-compose | all three | Day 1
2 | A-003…A-009 | Baseline schema | Ayush — seeds & entities | Day 3
3 | A-012 | dev-noauth profile | all three — any authenticated endpoint | Day 10
4 | A-034 | ScopeResolver | Debashis — socket authorisation mirrors it | Week 7
5 | A-040…A-042 | Append-only + hash chain | Divyansh — transitions write to those tables | Week 9
6 | B-001…B-004 | Seed data | all three — realistic local data | Day 7
7 | B-007 | Fixture corpus | Divyansh + Debashis — ribbon & SLA testing | Day 10
8 | B-021 | Priority master | Divyansh — priority dropdown | Week 5
9 | B-022 | Notification templates | Debashis — mail engine | Week 8
Ownership & Dependencies
3

## Slide 5
The 17 cross-stream dependencies · 2 of 2
# | Blocker | What it is | Who waits on it | Needed
10 | B-024 | Working-hours service | Debashis — every SLA calculation · Divyansh — stage durations | Week 3
11 | B-039…B-043 | Workflow templates | Divyansh — transitions need stage definitions | Week 9
12 | B-025…B-029 | Client master | Divyansh — client dropdown · Shivendra — client widget | Week 7
13 | C-042…C-049 | Transition service | Shivendra — ribbon widgets · Debashis — live push | Week 11
14 | C-003 | Component library | all three — every screen in every stream | Day 7
15 | D-001 | OpenAPI contract | all three — all API work | Week 1
16 | D-004 | MSW mock server | Divyansh — the entire frontend before APIs exist | Day 5
17 | D-012…D-014 | STOMP infrastructure | Divyansh — live ribbon advance | Week 10
Shivendra is upstream of everyone and blocked by nobody. Ayush carries four of the seventeen edges — more than anyone else.
Ownership & Dependencies
4

## Slide 6
The critical path
Eight links. Delay anywhere on this chain delays go-live one-for-one
A-003…A-009
Schema
wk 1
Shivendra
A-008
Immutability triggers
wk 2
Shivendra
A-040…A-042
Append-only + hash chain
wk 8–9
Shivendra
C-042…C-049
Transition service
wk 10–11
Divyansh
C-055…C-058
Journey roll-up
wk 11
Divyansh
A-058
Ribbon dashboard widgets
wk 12–14
Shivendra
E2E
Walkthrough A end to end
wk 15–16
Divyansh
Go-live
Hardening, UAT
wk 17–18
all four
THE MOST FRAGILE HANDOFF
A-042 → C-042, week 9. Divyansh cannot start the transition service until the hash chain is finished and proven, because his service writes into those append-only tables.
OFF THE CRITICAL PATH — HAS SLACK
Client master · Excel import · reports · chat · notification centre · browser push.
These can absorb delay without moving go-live.
Ownership & Dependencies
5

## Slide 7
18 weeks, four lanes
Bars are work. Arrows are the moments one developer hands something to another
1
3
5
7
9
11
13
15
17
WEEK
A · Shivendra
schema · triggers · CI
auth · scope guard · matrix
immutability core
dashboard · reports
hardening
B · Ayush
seeds · entities · fixtures
masters · clients · import · workflow
ribbon UI with C
reports · Resource 360
UAT
C · Divyansh
design system
create · list · detail · comments
transitions · ribbon
journey · stage queue
E2E
UAT
D · Debashis
contract · mocks
outbox · STOMP
SLA · escalation · mail
chat · live ribbon
UAT
Red and amber arrows at week 10 are the convergence: the transition service needs Shivendra's hash chain AND Ayush's stage definitions before it can start.
Weeks 3–7 and 12–16 are fully parallel — nobody blocks anybody. Weeks 1–2 and 8–11 carry every handoff.
Ownership & Dependencies
6

## Slide 8
Week 9 — the one convergence to protect
Two upstream owners, one downstream task, sitting on the critical path
A-040 … A-042
Append-only services + per-ticket hash chain
Shivendra
B-039 … B-043
Workflow templates + stage definitions
Ayush
C-042 … C-049
Transition service — the Workflow Ribbon
Divyansh · week 10–11 · ON THE CRITICAL PATH
IF EITHER IS LATE
Give Divyansh C-059…C-064 — History and Attachments tabs, stage queue, bulk reassignment, ticket links. They depend on nothing and keep him productive while the blockers clear.
Ownership & Dependencies
7

## Slide 9
If you are blocked, do this
Nobody should ever idle — every stream has independent fallback work
Owner | Blocked on | Pick up instead
Shivendra | — nothing blocks him | He is upstream of everyone
Ayush | A's schema, days 1–2 | Design the seed content — permission matrix, 11 task types, 4 priorities, 3 workflow templates. It comes from the blueprint, not the schema
Ayush | A's schema, later | B-030…B-038 Excel import engine — pure POI work, touches no EduTrack table
Divyansh | D's mocks, days 1–4 | C-002…C-004 design tokens, component library, Storybook — no data needed
Divyansh | A-042 or B-043, week 9 | C-059…C-064 tabs, stage queue, bulk reassign, ticket links
Debashis | B-024 working-hours, week 3 | D-010…D-015 outbox, ShedLock, STOMP, channel interceptor
Debashis | C's transitions, week 11 | D-040…D-046 notification centre, preference matrix, offline queue
Ownership & Dependencies
8

## Slide 10
Three habits that prevent imaginary blockers
Each of these has stalled real teams on this exact shape of project
Never wait for an API — use the mocks
D-004 exists so the full ticket detail page, ribbon included, can be built before a single ticket endpoint is written. When the real endpoint lands, the only change is a flag.
Never wait for auth — use dev-noauth
And never write your own filtering as a workaround. That is how a temporary shortcut becomes a permanent security hole — the top risk in blueprint §17.
Never write your own date maths
Every SLA, duration, breach and utilisation figure routes through B-024. Four private implementations of "working hours" produce four different answers, and the disagreement surfaces in a client dispute.
Ownership & Dependencies
9

## Slide 11
How to use this
Daily
Check whether anything you own appears in the 17-edge register. If it does, somebody is waiting on you.
When blocked
Go to the fallback table. There is always independent work — idling is never the right answer.
At milestone boundaries
Review the register when develop is promoted to main. Tasks move between streams; the map must move with them.
When adding a task
If it crosses a stream boundary, add it to §2 in the same pull request.
A dependency register that has drifted is worse than none — people trust it and are wrong.
docs/DEPENDENCIES.md · docs/streams/STREAM-A…D.md · docs/TEAM-PLAN.md