## Tasks
Stage | Task Name | Description | TAT Days | Requires Sign-off (Y/N) | Depends On Task
Configuration | Login Configuration | Create the admin and teacher logins and hand over first-use credentials. | 1 | N
Configuration | School Configuration | Register the school profile, branding, address and academic contact. | 1 | N | Login Configuration
Configuration | Academic Year & Term Setup | Define the academic year, terms and the working calendar for the session. | 1 | N | School Configuration
Configuration | Class, Section & Subject Setup | Create the class and section grid and map the subject list to each class. | 2 | N | Academic Year & Term Setup
Data Migration | Student Master Data Migration | Load the student master from existing records and reconcile counts. | 3 | Y | Class, Section & Subject Setup
Data Migration | Staff & Teacher Data Migration | Load staff records and map teachers to subjects and sections. | 2 | N | Class, Section & Subject Setup
Data Migration | Historical Marks & Attendance Migration | Import prior-year marks and attendance so trend reports have a baseline. | 3 | Y | Student Master Data Migration
Reports | Report Card Template Configuration | Build the report card format, grading scale and remarks blocks. | 2 | Y | Historical Marks & Attendance Migration
Reports | Standard Report Pack Enablement | Switch on attendance, fee-due and performance reports for each role. | 1 | N | Report Card Template Configuration
Training | Admin & Principal Training | Walkthrough of configuration, approvals and the reporting pack. | 1 | N | Standard Report Pack Enablement
Training | Teacher Training | Attendance marking, marks entry and report card generation for teaching staff. | 2 | N | Admin & Principal Training
Training | Front Office Training | Admissions, enquiry capture and fee counter operations. | 1 | N | Admin & Principal Training
Communication | SMS & Email Gateway Configuration | Connect the SMS sender ID and SMTP account, then send a test message. | 1 | N | School Configuration
Communication | Notification Template Setup | Configure absentee, fee-reminder and circular templates. | 1 | N | SMS & Email Gateway Configuration
Third Party Integration | Payment Gateway Integration | Wire the payment gateway, run a test transaction and verify the refund flow. | 2 | Y | School Configuration
Third Party Integration | Biometric Attendance Device Integration | Connect biometric devices and verify punches reach the attendance module. | 2 | N | Staff & Teacher Data Migration
Web/App Reflection | Website Data Sync | Publish notices, gallery and circulars from the SIS to the school website. | 1 | N | Standard Report Pack Enablement
Web/App Reflection | Mobile App Rollout & UAT Sign-off | Release the parent and teacher app, run UAT and collect the go-live sign-off. | 2 | Y | Teacher Training

## Task List
Task Name | Item Label | Mandatory (Y/N)
Login Configuration | Admin Login | Y
Login Configuration | Teacher Login | Y
School Configuration | Create School | Y
School Configuration | Assign SPOC | Y
Academic Year & Term Setup | Academic year created | Y
Academic Year & Term Setup | Terms and exam cycles defined | Y
Academic Year & Term Setup | Holiday calendar uploaded | N
Class, Section & Subject Setup | Classes and sections created | Y
Class, Section & Subject Setup | Subjects mapped to each class | Y
Class, Section & Subject Setup | Class teacher assigned | Y
Student Master Data Migration | Student count reconciled with client | Y
Student Master Data Migration | Duplicate admission numbers resolved | Y
Student Master Data Migration | Parent contact numbers verified | Y
Staff & Teacher Data Migration | Staff records loaded | Y
Staff & Teacher Data Migration | Teacher-subject mapping confirmed | Y
Historical Marks & Attendance Migration | Prior-year marks imported | Y
Historical Marks & Attendance Migration | Attendance totals match source | Y
Report Card Template Configuration | Grading scale configured | Y
Report Card Template Configuration | Sample report card approved by school | Y
Standard Report Pack Enablement | Attendance report verified | Y
Standard Report Pack Enablement | Fee-due report verified | Y
Standard Report Pack Enablement | Role-wise report access checked | N
Admin & Principal Training | Session delivered | Y
Admin & Principal Training | Attendance sheet collected | Y
Teacher Training | Attendance marking demonstrated | Y
Teacher Training | Marks entry demonstrated | Y
Teacher Training | Feedback form collected | N
Front Office Training | Admission flow demonstrated | Y
Front Office Training | Fee counter flow demonstrated | Y
SMS & Email Gateway Configuration | Sender ID approved | Y
SMS & Email Gateway Configuration | Test SMS delivered | Y
SMS & Email Gateway Configuration | Test email delivered | Y
Notification Template Setup | Absentee alert template approved | Y
Notification Template Setup | Fee reminder template approved | Y
Notification Template Setup | Circular template approved | N
Payment Gateway Integration | Merchant credentials configured | Y
Payment Gateway Integration | Test transaction successful | Y
Payment Gateway Integration | Refund flow verified | Y
Biometric Attendance Device Integration | Devices reachable on school network | Y
Biometric Attendance Device Integration | Punch data syncing to SIS | Y
Website Data Sync | Notices publishing to website | Y
Website Data Sync | Gallery sync verified | N
Mobile App Rollout & UAT Sign-off | Parent app login verified | Y
Mobile App Rollout & UAT Sign-off | Teacher app login verified | Y
Mobile App Rollout & UAT Sign-off | UAT defects closed | Y

## Document Checklist
Task Name | Document Label | Required (Y/N)
Login Configuration | Document | Y
Login Configuration | Credential handover acknowledgement | Y
School Configuration | School profile form (signed) | Y
School Configuration | School logo and letterhead | N
Academic Year & Term Setup | Academic calendar (PDF) | Y
Class, Section & Subject Setup | Class-subject mapping sheet | Y
Student Master Data Migration | Student master source file | Y
Student Master Data Migration | Data reconciliation sheet (signed) | Y
Staff & Teacher Data Migration | Staff master source file | Y
Historical Marks & Attendance Migration | Previous year marks sheet | Y
Historical Marks & Attendance Migration | Previous year attendance register | N
Report Card Template Configuration | Approved report card sample | Y
Standard Report Pack Enablement | Report verification checklist (signed) | N
Admin & Principal Training | Training attendance sheet | Y
Teacher Training | Training attendance sheet | Y
Teacher Training | Training feedback forms | N
Front Office Training | Training attendance sheet | Y
SMS & Email Gateway Configuration | Sender ID approval letter | Y
SMS & Email Gateway Configuration | SMTP credentials form | Y
Notification Template Setup | Approved template pack | N
Payment Gateway Integration | Merchant onboarding agreement | Y
Payment Gateway Integration | Test transaction receipt | Y
Biometric Attendance Device Integration | Device inventory and IP list | Y
Website Data Sync | Website access credentials form | Y
Mobile App Rollout & UAT Sign-off | UAT sign-off form (signed) | Y
Mobile App Rollout & UAT Sign-off | Go-live approval email | Y

## Instructions
Student Information System - sample task import (OB-07)
Import into a DRAFT version only. An Active version is refused.
Open the Module Service, press 'Begin revision', then 'Import tasks'.
This file REPLACES the draft's entire task tree. The two tasks already
present (Login Configuration, School Configuration) and their checklist
rows are included here, so nothing is lost.
Valid Stage values for this Module Service:
- Configuration
- Data Migration
- Reports
- Training
- Communication
- Third Party Integration
- Web/App Reflection
Rules: Task Name unique; TAT Days a whole number > 0;
'Depends On Task' must name a task listed ABOVE it on the Tasks sheet;
Task Name on the other two sheets must match a Tasks row exactly.
Blank Mandatory/Required means Y. Blank Requires Sign-off means N.